 -
 -
 -
 -
 -
 -
 -
 -
 -
 -
 -
 -
 -
 -
## WBS(全体)
プロジェクト名					フリマシステム		スタート日				2023/6/20			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42
チーム名					チーム3		氏名	田村、大下、竹内、山岳、木下、小野
ID			タスク名				担当	Status	期間 / (日)	予定/ / 実績	開始	終了	注	6	月										7	月
														20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
														火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月
0	0	0	スタッフによる模擬演習の進め方について説明				スタッフ	完	1	-	06/20	06/20		1
0	1	0	常に次のフェーズを開始する前日にタスクや役割を記載する				田村	完	1	-	06/20	06/20		1
1	0	0	要件定義			【目安工数：～0.5日】	対応中	/	1	予定	06/20	06/20	*	1
1	1	0		体制決め（リーダー決め）			完	完	1	-	06/20	06/20		1
1	2	0		顧客要望ヒアリング			完	完	1	-	06/20	06/20		1
1	3	0		要件定義書			対応中	/	1	-	06/20	06/20	*	1
1	3	1			要件定義書作成		竹内	/	1	予定	06/20	06/20	*	1
1	3	2						完	1	実績	06/20	06/20		1
1	3	3			顧客の要望・要件についての質問表の作成		竹内	/	1	予定	06/20	06/20	*	1
1	3	4						完	1	実績	06/20	06/20		1
1	4	0		★顧客へ報告 ※（まとめた要件を説明）			田村	/	1	予定	06/20	06/20	*	1
1	4	1					田村大下竹内	完	1	実績	06/20	06/20		1
2	0	0	画面設計			【目安工数：～1日】	/	/	2	予定	06/20	06/21		1	1
2	1	0		画面遷移図(一画面） ※（エクセル1シート）			全員	/	1	予定	06/20	06/20	*	1
2	1	1					山岳	対応中	1	実績	06/20		*
2	2	0		画面遷移図の概要【権限別】			/	/	1	-	06/21	06/21			1
2	2	1			顧客側画面遷移図の概要 ※（エクセル1シート）		全員	/	1	予定	06/21	06/21			1
2	2	2					山岳	対応中	1	実績	06/21		*
2	2	3			管理者側画面遷移図の概要 ※（エクセル1シート）		全員	/	1	予定	06/21	06/21			1
2	2	4					山岳	対応中	1	実績	06/21		*
2	3	0		画面一覧＆概要作成 (※エクセル1シート)			全員	/	1	予定	06/21	06/21			1
2	3	1					山岳	対応中	1	実績	06/21		*
2	4	0		★顧客へ報告※(画面遷移図の説明)※次のHTMLデモと一緒に報告してもよい			大下	/	1	予定	06/21	06/21			1
2	4	1						skip	1	実績			*
2	5	0		★上司へ提出（該当の画面遷移図をファイルで提出）			竹内	/	1	予定	06/21	06/21			1
2	5	1						未着	1	実績			*
2	5	0		別シート「WBS(HTML)」に画面一覧と担当を記載			山岳	/	1	予定	06/21	06/21			1
2	5	0					山岳	完	1	実績
2	6	0		HTMLで画面作成			/	/	2	-	06/21	06/22			1	1
2	6	1			HTMLによる顧客側画面作成		全員	/	2	予定	06/21	06/22			1	1
2	6	2						対応中	2	実績			*
2	6	3			HTMLによる管理者側画面作成		全員	/	2	予定	06/21	06/22			1	1
2	6	4						対応中	2	実績			*
2	7	0		★顧客へ報告※(HTMLによる動きをデモ)※Excel形式の画面遷移図も提出			小野	/	1	予定	06/22	06/22				1
2	7	1					小野田村	予定	1	実績	06/21		*
3	0	0	内部設計			【目安工数：～0.5日】	/	/	2	予定	06/22	06/23				1	1
3	1	0		機能一覧＆概要			全員	/	1	予定	06/22	06/22				1
3	1	1						未着	1	実績			*
3	2	0		テーブル設計			/	/	2	-	06/22	06/23				1	1
3	2	1			データの洗い出し（作成した画面を基に）		全員	/	1	予定	06/22	06/22				1
3	2	2						未着	1	実績			*
3	2	3			テーブルの論理設計（ER図）の作成		全員	/	1	予定	06/23	06/23					1
3	2	4						未着	1	実績			*
3	2	5			テーブルの物理設計		全員	/	1	予定	06/23	06/23					1
3	2	6						未着	1	実績			*
3	3	0		Eclipseファイル構成			小野	/	1	予定	06/23	06/23					1
3	3	1						未着	1	実績			*
3	4	0		サーブレットのマッピング設計			竹内	/	1	予定	06/23	06/23					1
3	4	1						未着	1	実績			*
3	5	0		MVCモデル図【権限別】 （※オプション）			/	保留	1	-
3	5	1			MVCモデル図作成(顧客側) （※オプション）			保留	1	-
3	5	2			MVCモデル図作成(管理者側) （※オプション）			保留	1	-
3	6	0		サーブレットの詳細設計 （※オプション）				保留	1	-
3	7	0		クラス図 （※オプション）				保留	1	-
3	8	0		シーケンス図 （※オプション）				保留	1	-
3	9	0		★画面＆内部設計書の一式をファイルで上司に提出			山岳	/	1	予定	06/23	06/23	*
3	9	1						未着	1	実績			*
3	10	0		前日にWBSの「製造」にタスクや担当を記載する			木下	/	1	予定	06/23	06/23	*
3	10	0						未着	1	実績			*
4	0	0	製造			【目安工数：～4日】	/	/	3	予定	06/26	06/28								1	1	1
4	1	0		「WBS製造、動作確認」シートに機能と担当を記載			竹内	/	1	予定	06/26	06/26								1
4	1	1						未着	1	実績			*
4	2	0		MySQLのDB及びテーブル作成			全員	/	1	予定	06/26	06/26								1
4	2	1						未着	1	実績			*
4	3	0		コーディング (※詳細は「製造」シートを参照）※一人最低1機能製造			全員	/	3	予定	06/26	06/28								1	1	1
4	3	1						未着	3	実績			*
4	4	0		単体テスト（プログラミングしながら実施）			全員	/	2	予定	06/26	06/27								1	1
4	4	1						未着	2	実績			*
4	5	0		テストフェーズについて説明 （※模擬演習の概要内にある）			スタッフ	未着	1	-	06/28	06/28										1
4	6	0		別シート「WBSテスト」シートに機能と担当を記載			大下	/	1	予定	06/27	06/27									1
4	6	1						未着	1	実績			*
4	7	0		総合テスト（シナリオテスト）作成			全員	/	1	予定	06/28	06/28										1
4	7	1						未着	1	実績			*
4	8	0			★テストケースのファイル提出＆上司に提出		木下	未着	1	予定	06/28	06/28										1
4	8	1							2	実績
4	9	0		※模擬演習2日前～終了日間の実施タスク確認(別紙PPT資料)			田村	未着	1	-	06/26	06/26								1
5	0	0	総合テスト			【工数：～0.5日】	/	/	2	予定	06/28	06/29										1	1
5	1	0		総合テスト（シナリオテスト）実施			/	/	1	予定	06/28	06/28										1
5	1	1			テスト実施結果として氏名と判定を記載		全員	/	1	予定	06/29	06/29											1
5	1	2						未着	1	実績			*
5	1	3			実施したテストエビデンス（※一人1シナリオのみ）		全員	/	1	予定	06/29	06/29											1
5	1	4						未着	1	実績			*
5	1	3			★テスト実施結果のファイル提出＆上司に提出		小野	/	1	予定	06/29	06/29											1
5	1	3						未着	1	実績			*
5	2	0		バグ修正			全員	/	1	予定	06/29	06/29											1
5	2	1						未着	1	実績			*
5	3	0		プレゼン資料ルールを精読 （※模擬演習の進め方資料内にある）			全員	/	1	予定	06/08	06/08	*
5	3	1						未着	1	実績			*
5	4	0		プレゼン資料作成			全員	/	2	予定	06/28	06/29										1	1
5	4	1						未着	1	実績			*
6	0	0	プレゼン			【目安工数：～0.5日】	/	/	1	-	06/30	06/30												1
6	1	0		★プレゼン実施（配布物：説明資料、WBS(全体,HTML,製造,テスト)			全員	未着	1	-	06/30	06/30												1
7	0	0	納品物提出（配布した資料（設計書を含む）一式）				田村	未着	1	-	06/30	06/30												1
END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END	END

## WBS記述例
プロジェクト名					神田美容院システム		スタート日				2023/6/20			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21
チーム名					チーム3		氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
ID			タスク名			担当者名を記述する	担当	Status	期間 / (日)	予定/ / 実績	開始	終了	注	6	月										7	月
			レベル１ / タスク											20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10
					レベル2 / タスク									火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月
0	0	0	スタッフによる模擬演習の進め方について説明				スタッフ	/	1	-	06/20	06/20	*			期間と開始日を入力することで / 自動的に色が設定されます。 / （※手動入力禁止！）
0	1	0	常に次のフェーズを開始する前日にタスクや役割を記載する				一郎	未着	1	-	06/20	06/20	*
1	0	0	要件定義			【目安工数：～0.5日】	/ / 開始日を記述する / 04/03の日付形式で入力 / （スタート日からの日程のみ入力可能）	/	1	予定	06/20	06/20	*
1	1	0		体制決め（リーダー決め）		レベル3 / タスク	/	/	1	-	06/20	06/20	*
1	2	0		顧客要望ヒアリング			/	/	1	-	06/20	06/20	*
1	3	0		要件定義書			/	/	1	-	06/20	06/20	*
1	3	1			要件定義書作成		一郎	/	1	予定	06/20	06/20	*
1	3	2						未着	1	実績		12/29	*
1	3	3			顧客の要望・要件についての質問表の作成	期間を記述する / (1以上の数字のみ / 入力可能）	一郎	/	1	予定	06/20	06/20	*
1	3	4						未着	1	実績		12/29	*
1	4	0		★顧客へ報告 ※（まとめた要件を説明）			一郎	/	1	予定	06/20	06/20	*			終了日は期間と開始に値を入れることで / 自動的に設定されます。 / （※手動入力禁止！）
1	4	1						未着	1	実績		12/29	*
2	0	0	画面設計			【目安工数：～1日】	/	/	2	予定	06/20	06/21	*
2	1	0		画面遷移図(一画面） ※（エクセル1シート）	ＩＤはタスク名に値を入力することで / 自動的に設定されます。 / （※手動入力禁止！）		一郎	/	1	予定	06/20	06/20	*
2	1	1						未着	1	実績		12/29	*
2	2	0		画面遷移図の概要【権限別】			/	/	1	-	06/20	06/20	*
2	2	1			顧客側画面遷移図の概要 ※（エクセル1シート）		二郎	/	1	予定	06/20	06/20	*
2	2	2						未着	1	実績		12/29	*
2	2	3			管理者側画面遷移図の概要 ※（エクセル1シート）		三郎	/	1	予定	06/20	06/20	*
2	2	4						未着	1	実績		12/29	*
2	3	0		画面一覧＆概要作成 (※エクセル1シート)			三郎	/	1	予定	06/20	06/20	*
2	3	1						未着	1	実績			*
2	4	0		★顧客へ報告※(画面遷移図の説明)※次のHTMLデモと一緒に報告してもよい			一郎	/	1	予定	06/20	06/20	*
2	4	1						未着	1	実績		12/29	*
2	5	0		★上司へ提出（該当の画面遷移図をファイルで提出）			一郎	/	1	予定	06/20	06/20	*

## WBS (HTML)
プロジェクト名					フリマシステム		スタート日				2023/6/20			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23
チーム名					チーム3		氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
ID			タスク名				担当	Status	予定/ / 実績	期間 / (日)	開始	終了	注	6	月										7	月
														20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12
														火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水
1	0	0	HTML						予定	2	06/20	06/21		1	1
1	1	0		共通
1	1	1			ログイン画面		大下	/	予定	1	06/20	06/20	*	1
1	1	2					大下	完	実績	1	06/21	06/21			1
1	1	3			エラー画面		竹内	/	予定	1	06/20	06/20	*	1
1	1	4					竹内	完	実績	1	06/21	06/21			1
1	2	0		管理者画面
1	2	1			メニュー画面		小野	/	予定	1	06/20	06/20	*	1
1	2	2					小野	完	実績	1	06/21	06/21			1
1	2	3			メッセージ一覧画面		小野	/	予定	1	06/21	06/21			1
1	2	4					小野	対応中	実績	1		12/29	*
1	2	5			メッセージ詳細画面		田村	/	予定	1	06/21	06/21			1
1	2	6						未着	実績	1		12/29	*
1	2	7			メッセージ作成画面		木下	/	予定	1	06/21	06/21			1
1	2	8					木下	完	実績	1	06/21	06/21
1	2	9			メッセージ下書き		大下	未着	予定	1	06/21	06/21
1	2	10							実績	1
1	2	11			ユーザー一覧画面		大下	/	予定	1	06/20	06/20		1
1	2	12					大下	完	実績	1	06/21	06/21
1	2	13			ユーザー詳細画面		竹内	/	予定	1	06/21	06/21			1
1	2	14					竹内	完	実績	1	06/21	06/21
1	2	15			出品一覧画面		山岳	/	予定	1	06/21	06/21			1
1	2	16					山岳	対応中	実績	1	06/20	06/20	*
1	2	17			出品詳細画面		田村	/	予定	1	06/21	06/21			1
1	2	18					田村	完	実績	1	06/21	06/21
1	2	19			売上状況画面		木下	/	予定	1	06/21	06/21			1
1	2	20						未着	実績	1		12/29	*
1	3	0		ユーザー(会員)画面
1	3	1			会員登録画面		田村	/	予定	1	06/20	06/20	*	1
1	3	2					田村	完	実績	1	06/21	06/21			1
1	3	3			メニュー画面		木下	/	予定	1	06/20	06/20	*	1
1	3	4					木下	完	実績	1	06/21	06/21			1
1	3	5			マイページ画面		竹内	/	予定	1	06/20	06/20	*	1
1	3	6					竹内	完	実績	1	06/21	06/21			1
1	3	7			プロフィール変更画面		山岳	/	予定	1	06/21	06/21			1
1	3	8						未着	実績	1		12/29	*
1	3	9			商品一覧画面		竹内	/	予定	1	06/20	06/20	*	1
1	3	10						対応中	実績	1	06/21	06/21			1
1	3	11			詳細情報画面		大下	/	予定	1	06/21	06/21			1
1	3	12						対応中	実績	1	06/21	06/21			1
1	3	13			購入確認		小野	/	予定	1	06/21	06/21			1
1	3	14						未着	実績	1			*
1	3	15			商品登録画面		木下	/	予定	1	06/20	06/20
1	3	16					木下	完	実績	1	06/21	06/21
1	3	17			出品一覧画面		小野	/	予定	1	06/21	06/21			1
1	3	18						完	実績	1	06/21	06/21
1	3	19			詳細情報画面		田村	/	予定	1	06/21	06/21			1
1	3	20					田村	完	実績	1	06/21	06/21
1	3	21			更新画面		大下	/	予定	1	06/21	06/21			1
1	3	22						未着	実績	1		12/29	*
1	3	23			購入履歴画面		竹内	/	予定	1	06/21	06/21			1
1	3	24					竹内	完	実績	1	06/21	06/21
1	3	25			注文詳細画面		山岳	/	予定	1	06/21	06/21			1
1	3	26						未着	実績	1		12/29	*
1	3	27			メッセージ一覧		田村	/	予定	1	06/21	06/21			1
1	3	28						未着	実績	1		12/29	*
1	3	29			メッセージ詳細画面		木下	/	予定	1	06/21	06/21			1
1	3	30					木下	完	実績	1	06/21	06/21
1	3	31			メッセージ作成画面		小野	/	予定	1	06/21	06/21			1
1	3	32						未着	実績	1		12/29	*
1	3	33			メッセージ下書き		小野	/	予定	1	06/21	06/21
1	3	34						未着	実績	1

																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
																									#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?

## WBS (①製造)
プロジェクト名					フリマシステム		スタート日				2023/6/20					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35
チーム名					チーム3		氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜						Javaファイル単位で工数を記載
ID			タスク名				担当	Status	予定/ / 実績	工数 / (h)		期間 / (日)	開始	終了	注	6	月										7	月
																20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
																火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水
1	0	0	DAOクラス						予定	16	h	1	06/21	06/21			1 / Javaファイル単位で開始日・終了日を記載
1	1	0		管理者情報DAO			一郎	/	予定	4	h	1	06/21	06/21			1
1	1	1						完	実績	3	h	1	06/21	06/21			1
1	2	0		注文情報DAO			二郎	/	予定	4	h	1	06/21	06/21			1
1	2	1						完	実績	5	h	1	06/21	06/21			1
1	3	0		xx			三郎	/	予定	4	h	1	06/21	06/21			1
1	3	1						完	実績	4	h	1	06/21	06/21			1
1	4	0		xx			四郎	/	予定	4	h	1	06/21	06/21			1
1	4	1						対応中	実績		h	1	06/21	06/21			1
					総数	2	セルには計算式が入っているが、うまく反映されない場合は直接、数字を入力
					完了数	3																						Eclipseのファイル構成をイメージしながら / タスクを考えると良いでしょう。
					残り	-1
					完了率(%)	150%

1	0	0	モデル（Bean）クラス (DTO オブジェクト用のクラス)						予定		h		06/21	06/21			1
1	1	0		データの入れ物としてのクラス（管理者情報）			一郎	/	予定		h	1	06/21	06/21			1
1	1	1						未着	実績		h	1		12/29
1	2	0		データの入れ物としてのクラス（注文情報）			二郎	/	予定		h	1	06/21	06/21			1
1	2	1						未着	実績		h	1		12/29
1	3	0		xx			三郎	/	予定		h	1	06/21	06/21			1
1	3	1						未着	実績		h	1		12/29	*
1	4	0		xx			四郎	/	予定		h	1	06/21	06/21			1
1	4	1						未着	実績		h	1		12/29	*
					総数	2
					完了数	0		HTML担当者とJSP担当者は異なってもよい / JSPファイルは、HTMLファイルにJSPをプログラミングしたものを意味します
					残り	2
					完了率(%)	0%

1	0	0	権限や機能単位 (※サーブレット・JSP)
2	0	0	共通						予定		h	3	06/21	06/23			1	1	1
2	1	0		共通画面ＪＳＰ			一郎	/	予定		h	1	06/23	06/23					1
2	1	1						未着	実績		h
2	2	0		エラー画面JSP			一郎	/	予定		h	1	06/23		*
2	2	1						未着	実績		h
2	3	0		一覧表示機能
2	3	1			一覧表示JSP		二郎	/	予定		h	1	06/21	06/21			1
2	3	2						未着	実績		h
2	3	3			商品一覧表示用サーブレット		二郎	/	予定		h
2	3	4						未着	実績		h
2	4	0		xx機能
2	4	1			xxJSP		二郎	/	予定		h	1	06/21	06/21			1
2	4	2						未着	実績		h
2	4	3			xx用サーブレット		二郎	/	予定		h
2	4	4						未着	実績		h
					総数	1
					完了数	0
					残り	1
					完了率（%）	0%

1	0	0	購入者(ユーザー)						予定	2	h	3	06/21	06/23			1	1	1
1	1	0		カート追加機能
1	1	1			カート追加機能用サーブレット		二郎	/	予定	1	h	1	06/21	06/21			1
1	1	2						未着	実績		h			12/29	*
1	1	3			カート追加完了JSP		二郎	/	予定	1	h	1 / JSPとサーブレットがペアで一人が製造すること。 / 製造作業を決める単位について / クリックして画面が表示されるまでの流れをセットで決める。 / その意味で、JSPとサーブレットはペアで担当することをお勧めする。	06/21	06/21			1
1	1	4						未着	実績		h			12/29	*
1	2	0		xx機能
1	2	1			xx		二郎	/	予定	2	h	1	06/22	06/22				1
1	2	2						未着	実績		h			12/29	*
1	2	3			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	2	4						未着	実績		h			12/29	*
1	2	5			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	2	6						未着	実績		h
					総数	0
					完了数	0
					残り	0
					完了率	#DIV/0!

1	0	0	管理者						予定		h	3	06/21	06/23			1	1	1
1	1	0		ログイン機能
1	1	1			ログイン処理用サーブレット		二郎	/	予定	1	h	1	06/21	06/21			1
1	1	2						未着	実績		h			12/29	*
1	1	3			ログインJSP		二郎	/	予定	1	h	1	06/21	06/21			1
1	1	4						未着	実績		h			12/29	*
1	2	0		xx機能
1	2	1			xx		二郎	/	予定	2	h	1	06/21	06/21			1
1	2	2						未着	実績		h			12/29	*
1	2	3			xx		二郎	/	予定	1	h	1	06/21	06/21			1
1	2	4						未着	実績		h			12/29	*
1	3	0		xx機能
1	3	1			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	3	2						未着	実績		h			12/29	*
1	3	3			xx		三郎	/	予定	1	h	1	06/21	06/21			1
1	3	4						未着	実績		h			12/29	*
1	4	0		xx機能
1	4	1			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	4	2						未着	実績		h			12/29	*
1	4	3			xx		三郎	/	予定	1	h	1	06/21	06/21			1
1	4	4						未着	実績		h			12/29	*
1	5	0		xx機能
1	5	1			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	5	2						未着	実績		h			12/29	*
1	5	3			xx		三郎	/	予定	1	h	1	06/21	06/21			1
1	5	4						未着	実績		h			12/29	*
1	6	0		xx機能
1	6	1			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	6	2						未着	実績		h			12/29	*
1	6	3			xx		三郎	/	予定	1	h	2	06/22	06/23				1	1
1	6	4						未着	実績		h			12/29	*
					総数(管理者)	0
					完了数	0
					残り	0
					完了率	#DIV/0!

				全体の進捗状況(目標：06/23日までに製造完了)
					総数(全体)	5
					完了数	3
					残り	2
					完了率	60%

## WBS (②動作確認)
プロジェクト名					フリマシステム		スタート日					2023/6/20			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37
チーム名					チーム3		氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
ID			タスク名				担当	Status	予定/ / 実績	工数 / (h)	期間 / (日)	開始	終了	注	6	月										7	月
															20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
															火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水
1	0	0	DAOクラス						予定	4	1	06/22	06/22				1
1	1	0		管理者情報DAO			一郎	未着	実績		1	06/22	06/22				1
1	2	0		注文情報DAO			一郎	未着	実績				12/29	*
1	3	0		xx			一郎	未着	実績				12/29	*
1	4	0		xx			一郎	未着	実績				12/29	*
					総数	4
					完了数	0
					残り	4
					完了率(%)	0%

1	0	0	モデル（Bean）クラス (DTO オブジェクト用のクラス)						予定				12/29
1	1	0		xx				未着	実績				12/29	*
1	2	0		xx				未着	実績				12/29	*
1	3	0		xx				未着	実績				12/29	*
1	4	0		xx				未着	実績				12/29	*
					総数	4
					完了数	0
					残り	4
					完了率(%)	0%

			権限や機能単位 (※サーブレット・JSP)
1	0	0	共通						予定				12/29
1	1	0		共通画面ＪＳＰ				未着	実績				12/29	*
1	2	0		エラー画面JSP				未着	実績				12/29	*
1	3	0		一覧表示機能
1	3	1			一覧表示JSP			未着	実績				12/29	*
1	3	2			商品一覧表示用サーブレット			未着	実績				12/29	*
1	4	0		xx機能
1	4	1			xxJSP			未着	実績				12/29	*
1	4	2			xx用サーブレット			未着	実績				12/29	*
					総数	2
					完了数	0
					残り	2
					完了率（%）	0%

1	0	0	購入者(ユーザー)						予定				12/29
1	1	0		カート追加機能
1	1	1			カート追加機能用サーブレット			未着	実績				12/29	*
1	1	2			カート追加完了JSP			未着	実績				12/29	*
1	2	0		xx機能
1	2	1			xx			未着	実績				12/29	*
1	2	2			xx			未着	実績				12/29	*
1	2	3			xx			未着	実績				12/29	*
					総数	0
					完了数	0
					残り	0
					完了率	#DIV/0!

			管理者						予定				12/29
	1	0		ログイン機能
					ログイン処理用サーブレット			未着	実績				12/29	*
					ログインJSP			未着	実績				12/29	*
				xx機能
					xx			未着	実績				12/29	*
					xx			未着	実績				12/29	*
				xx機能
					xx			未着	実績				12/29	*
					xx			未着	実績				12/29	*
				xx機能
					xx			未着	実績				12/29	*
					xx			未着	実績				12/29	*
				xx機能
					xx			未着	実績				12/29	*
					xx			未着	実績				12/29	*
				xx機能
					xx			未着	実績				12/29	*
					xx			未着	実績				12/29	*
					総数(管理者)	0.5
					完了数	0
					残り	0.5
					完了率	0%

				全体の進捗状況(目標：06/23日までに製造完了)
					総数(全体)	10.5
					完了数	0
					残り	10.5
					完了率	0%

## WBS (③最終修正・追加)
プロジェクト名					フリマシステム		スタート日		2023/6/20					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37
チーム名					チーム3		氏名		大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
ID			タスク名				修正内容	担当	Status	予定/ / 実績	工数 / (h)	期間 / (日)	開始	終了	注	6	月					7	月
				20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
				火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水
1	0	0	DAOクラス					予定				12/29	開始の日時と期間を入力
1	0	1					予定				12/29
1	0	2					実績				12/29
1	0	3					予定				12/29
1	0	4					実績				12/29			修正が発生したらこのシートに記載する
1	0	5					予定				12/29
1	0	6					具体的な修正内容も記載			実績				12/29
1	0	7					予定				12/29
1	0	8					実績				12/29
				総数	0
				完了数	0
				残り	0
				完了率(%)	#DIV/0!

1	0	0	モデル（Bean）クラス (DTO オブジェクト用のクラス)					予定				12/29
1	0	1					予定				12/29
1	0	2					実績				12/29
1	0	3					予定				12/29
1	0	4					実績				12/29
1	0	5					予定				12/29
1	0	6					実績				12/29
1	0	7					予定				12/29
1	0	8					実績				12/29
				総数	0
				完了数	0
				残り	0
				完了率(%)	#DIV/0!

			権限や機能単位 (※サーブレット・JSP)
1	0	0	共通					予定				12/29
1	0	1					予定				12/29
1	0	2					実績				12/29
1	1	0		xx機能
1	1	1					予定				12/29
1	1	2					実績				12/29
1	2	0		xx機能
1	2	1					予定				12/29
1	2	2					実績				12/29
				総数	0
				完了数	0
				残り	0
				完了率（%）	#DIV/0!

1	0	0	購入者(ユーザー)					予定				12/29
1	1	0		xx機能
1	1	1					予定				12/29
1	1	2					実績				12/29
1	2	0		xx機能
1	2	1					予定				12/29
1	2	2					実績				12/29
				総数	0
				完了数	0
				残り	0
				完了率	#DIV/0!

1	0	0	管理者					予定				12/29
1	1	0		xx機能
1	1	1					予定				12/29
1	1	2					実績				12/29
1	2	0		xx機能
1	2	1					予定				12/29
1	2	2					実績				12/29
1	3	0		xx機能
1	3	1					予定				12/29
1	3	2					実績				12/29
1	4	0		xx機能
1	4	1					予定				12/29
1	4	2					実績				12/29
				総数(管理者)	0
				完了数	0
				残り	0
				完了率	#DIV/0!

				全体の進捗状況(目標：06/23日までに製造完了)
				総数(全体)	0
				完了数	0
				残り	0
				完了率	#DIV/0!

## WBS (テスト)
プロジェクト名					フリマシステム		スタート日					2023/6/20			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37
チーム名					チーム3		氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
ID			タスク名				担当	Status	予定/ / 実績	工数 / (分)	期間 / (日)	開始	終了	注	6	月										7	月
															20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
															火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水	木	金	土	日	月	火	水
1	0	0	シナリオ（総合）テストケース一覧作成				一郎	未着	予定				12/29	*

1	0	0	シナリオ（総合）テストケース作成						予定				12/29
1	1	0		ｘｘｘｘ機能			一郎		予定				12/29
1	1	1						未着	実績				12/29	*
1	2	0		ｘｘｘｘ機能					予定				12/29
1	2	1						未着	実績				12/29	*
1	3	0		ｘｘｘｘ					予定				12/29
1	3	1						未着	実績				12/29	*
1	4	0		ｘｘｘｘ					予定				12/29
1	4	1						未着	実績				12/29	*
1	5	0		ｘｘｘｘ					予定				12/29
1	5	1						未着	実績				12/29	*
1	6	0		ｘｘｘｘ					予定				12/29
1	6	1						未着	実績				12/29	*
1	7	0		ｘｘｘｘ					予定				12/29
1	7	1						未着	実績				12/29	*
1	8	0		ｘｘｘｘ					予定				12/29
1	8	1						未着	実績				12/29	*

1	0	0	シナリオ（総合）テスト実施（1回目）						予定				12/29
1	1	0		ｘｘｘｘ機能			一郎		予定				12/29
1	1	1						未着	実績				12/29	*
1	2	0		ｘｘｘｘ機能					予定				12/29
1	2	1						未着	実績				12/29	*
1	3	0		ｘｘｘｘ					予定				12/29
1	3	1						未着	実績				12/29	*
1	4	0		ｘｘｘｘ					予定				12/29
1	4	1						未着	実績				12/29	*
1	5	0		ｘｘｘｘ					予定				12/29
1	5	1						未着	実績				12/29	*
1	6	0		ｘｘｘｘ					予定				12/29
1	6	1						未着	実績				12/29	*
1	7	0		ｘｘｘｘ					予定				12/29
1	7	1						未着	実績				12/29	*
1	8	0		ｘｘｘｘ					予定				12/29
1	8	1						未着	実績				12/29	*

1	0	0	シナリオ（総合）テスト実施（2回目）						予定				12/29
1	1	0		ｘｘｘｘ機能			一郎		予定				12/29
1	1	1						未着	実績				12/29	*
1	2	0		ｘｘｘｘ機能					予定				12/29
1	2	1						未着	実績				12/29	*
1	3	0		ｘｘｘｘ					予定				12/29
1	3	1						未着	実績				12/29	*
1	4	0		ｘｘｘｘ					予定				12/29
1	4	1						未着	実績				12/29	*
1	5	0		ｘｘｘｘ					予定				12/29
1	5	1						未着	実績				12/29	*
1	6	0		ｘｘｘｘ					予定				12/29
1	6	1						未着	実績				12/29	*
1	7	0		ｘｘｘｘ					予定				12/29
1	7	1						未着	実績				12/29	*
1	8	0		ｘｘｘｘ					予定				12/29
1	8	1						未着	実績				12/29	*

## 課題管理表
				<<課題管理表>>
	課題件数	2
	解決済件数	0
	未解決件数	2

項番	優先度	記入日	記入者	カテゴリ	課題内容	問合先	社内 / 担当者	ステータス	回答日	回答者	回答内容	備考
1	中	2015/6/15	江田颯	設計	(例)議事録に関して、顧客が信頼できるような書き方が把握できていない。 / 可能な限り丁寧に書こうとするとそちらに時間が取られてしまい、設計が / 厳かになってしまう	社内					サンプル
2	中	2015/8/18	鈴木一紘		メインメニュー画面の出勤登録処理と2ヶ月、3か月分のカレンダー表示ができておらず、内部設計の計画に影響を与えてしまう。
3	高
4
5
6
7
8
9
10
11
12
13
14

## WBS初期設定
プロジェクト開始日	2023/6/20	プロジェクト開始日を記入する / 例）2016/06/03
プロジェクト名	フリマシステム	プロジェクト開始日を記入する / 例）2016/06/03
チーム名	チーム3	プロジェクト開始日を記入する / 例）2016/06/03
氏名	大下裕司、竹内誠、山岳亮介、田村匠、木下智絵、小野茜
	プロジェクト名を記入する / 例） / 神田美容院システム